# Pets of [City] — MVP Execution Kit

Operational companion to the MVP Proof-of-Concept Plan. Three parts: (1) a one-page pilot brief for board/staff buy-in, (2) a week-by-week launch checklist with owners, and (3) a KPI dashboard pairing business metrics with mission-amplification metrics (incl. the vet-wellness-visit metric). Run as an internal APPA program — no new entity. ~5 months, ~$200K.

MVP core (4, confirmed): Chattanooga (HQ), Brentwood/Franklin, Columbia, Raleigh — a coherent Southeast region. Warm vet relationships in Chattanooga & Raleigh (source Columbia/Brentwood intros pre-launch). Chattanooga (HQ) is the lead/platform-seed market. Expansion (~10 = a region): Southeast → Midwest (KC/Omaha/Wichita) → Texas (San Antonio/Waco/Austin). See [PoC-Pilot-City-Shortlist.md → Confirmed MVP core](./PoC-Pilot-City-Shortlist.md).

# Part 1 — One-Page Pilot Brief

What: A lean, ~5-month pilot of Pets of [City] — a hyper-local pet utility + community + data platform (weekly newsletter as the funnel; directory, adoption, housing, events, discount card, data panel) — in 4 Southeast markets: Chattanooga (HQ/lead), Brentwood/Franklin (member-brand HQ hub), Columbia, Raleigh.

Why (the Rosetta Stone): Prove we can turn advocacy into a profit center — solving pet-care's biggest problems (declining vet visits, pet-inclusive housing, independent-retail/live-sales threats, stalled ownership) *and making money doing it* — while giving APPA its first local delivery channel for the ~$2.5M/year it already spends on mission.

Why now: Validate the riskiest assumptions cheaply before incorporating APPA Ventures or committing the staged ~$3M. A weak pilot saves ~$3M and a year.

Scope & structure: Internal APPA program (no entity); AI-assisted, human-edited, disclosed content; high-margin-line + platform-seed tests concentrated in Chattanooga (HQ); consent/panel opt-in from day one.

Budget: ~$200K (operating-budget line; under any entity-formation threshold).

What we're testing:

H1 Demand (cheap, engaged subscribers) · H2 Engagement (opens/reads) · H3 Monetization — high-margin lines (insurance lead-gen, operator-side housing, paid lead-gen) · H4 Ops & quality (AI+human, one editor) · H5 Platform-seed (discount card, event, product-JV, panel opt-in)

Mission-amplification (the "why"): vet-wellness-visit promotion, vet/shelter/independent-retailer/housing participation, advocacy reach.

Go decision: GO to incorporate + fund if ≥3 of 4 markets clear subscriber + engagement thresholds and monetization is validated in ≥1 market including ≥1 high-margin line (not ads alone). H5 + mission signals strengthen the case but don't gate. (Full thresholds: Part 3.)

The ask: Approve the ~$200K pilot budget and a fractional project lead + Chattanooga (HQ) editor, with a board decision gate at ~Month 5.

Owner: [Project Lead] · Sponsor: [APPA CEO] · Decision body: [APPA Board / Exec]

# Part 2 — Week-by-Week Launch Checklist

Team (lean, mostly contract): PM = project lead · ED = Chattanooga (HQ) community editor (PT) · AI = content/AI contractor · DES = freelance designer · PERF = performance-marketing contractor · APPA = APPA staff/leadership (partnerships) · ADV = media advisor (optional).

### Phase 0 — Setup (Weeks 1–4)

| Wk | Tasks | Owner |
| --- | --- | --- |
| 1 | Approve budget; assign PM; confirm 4 markets; confirm Chattanooga (HQ) editor; kickoff + RACI | PM/APPA |
| 1–2 | Stand up newsletter platform (beehiiv-class) + analytics; set up domains/sender auth (deliverability) | PM/AI |
| 1–2 | Build subscribe flow with panel opt-in / consent (CCPA-class) + privacy terms | PM/AI |
| 2 | Brand placeholder, logo, email + landing-page templates | DES |
| 2–3 | Content templates + AI-assisted draft workflow with mandatory human/editorial review; no-vet-advice + brand-safety checklist | AI/ED |
| 2–3 | 4-market content calendars; source local events/adoption/housing/deals feeds (owned/licensed, no scraping) | ED/AI |
| 3 | Target lists: local advertisers, vets (incl. sourcing Columbia/Brentwood warm intros), groomers/boarders, shelters/rescues, property managers, independent retailers | ED/APPA |
| 3 | Set up pet-insurance affiliate/lead-gen placement (multi-carrier); pay-per-lead tooling | PM |
| 3–4 | Discount-card pilot setup (digital wallet, wellness-visit anchor, redemption tracking) — Chattanooga | PM/ED |
| 3–4 | Metrics dashboard (Part 3) live; baseline targets set | PM |
| 4 | Begin partnership outreach: shelters, vets, member-brand sponsor(s), housing operators | APPA/ED |

### Phase 1 — Soft launch (Weeks 5–7)

| Wk | Tasks | Owner |
| --- | --- | --- |
| 5 | First weekly sends in all 4 markets; QA content/links/deliverability | ED/AI |
| 5 | Start paid acquisition (test 2–3 channels); seed via shelters/vets/social | PERF/ED |
| 5–7 | Weekly cadence; monitor open/click/unsub + panel opt-in rate; iterate creative | ED/AI |
| 6 | Welcome/onboarding sequence live (fights month-1 churn) | AI |
| 6–7 | First sponsor conversations; confirm ≥1 member-brand national sponsor pipeline | APPA/PM |
| 7 | Phase-1 review: CAC, opens, opt-in vs. baseline; adjust | PM |

### Phase 2 — Grow & monetize (Weeks 8–16)

| Wk | Tasks | Owner |
| --- | --- | --- |
| 8–16 | Scale acquisition to subscriber targets; manage frequency/preferences (fatigue watch) | PERF/ED |
| 8–10 | Chattanooga high-margin tests: launch insurance lead-gen unit (esp. to new adopters); measure leads | PM/ED |
| 9–12 | Operator-side housing: pitch 3–5 property managers (listings/tools); land paid interest | APPA/ED |
| 9–12 | Paid directory / pay-per-lead with vets/groomers (Chattanooga + Raleigh, warm vet markets) | ED |
| 10–14 | Discount card live (Chattanooga): onboard 10–20 businesses; consumer sign-ups; wellness-visit redemptions tracked | ED/PM |
| 11–14 | Mission-amplification push: vet wellness-visit promotion (Chattanooga/Raleigh); weekly adoptable-pets/shelter features; independent-retailer spotlights | ED/APPA |
| 12–14 | One sponsored community event (Chattanooga) — adoption day/yappy hour; ≥1 paying sponsor | ED |
| 12–15 | Product-JV "new-owner starter kit" pilot with a member brand | APPA/PM |
| 14–16 | Lock member-brand national sponsor; gather LOIs/pilot revenue across lines | APPA/PM |
| 16 | Data cut for analysis; subscriber + monetization + mission tallies | PM |

### Phase 3 — Measure & decide (Weeks 17–22)

| Wk | Tasks | Owner |
| --- | --- | --- |
| 17–19 | Analyze all KPIs vs. thresholds (Part 3); per-market + overall; cohort/fatigue analysis | PM/ADV |
| 18–20 | Synthesize learnings; refine the §C/§D assumptions with real data | PM |
| 20–21 | Board decision memo (go/no-go to incorporate Ventures + commit ~$3M + scale the Southeast region) | PM/APPA |
| 22 | Board decision gate; if GO → kick off incorporation + regional-expansion sequencing | APPA Board |

# Part 3 — KPI Dashboard (business + mission)

Track per market and overall; review weekly (leading) and at the Month-5 gate (decision). Targets per market by end of pilot unless noted.

### A. Business — audience & engagement

| KPI | Target | How measured |
| --- | --- | --- |
| Subscribers | 3,000–5,000 | Platform |
| Subscriber CAC | ≤ $1.50 | Spend ÷ net adds |
| Open rate | ≥ 40% | Platform |
| Click rate | ≥ 3% | Platform |
| Unsubscribe / send | < 0.5% | Platform |
| Engagement durability | Open rate holds (no steep decay) | Cohort trend (fatigue read) |
| Panel opt-in | ≥ 25–40% of subs | Consent flow |

### B. Business — monetization (high-margin lines first)

| KPI | Target | How measured |
| --- | --- | --- |
| Insurance lead-gen | Measurable leads at viable effective payout ($25–152/policy benchmark) | Affiliate dashboard |
| Operator-side housing | ≥ 2–3 property managers express paid interest | Sales pipeline |
| Paid directory / pay-per-lead | Paying vet/groomer advertisers; ~$40/lead benchmark | CRM |
| Member-brand sponsor | ≥ 1 national sponsor signed/committed | Sales |
| Discount card | ≥ 10–20 businesses + consumer sign-ups + first redemptions | Card platform |
| Event | ≥ breakeven with ≥ 1 paying sponsor | Event P&L |
| Product-JV starter kit | Sells with ≥ 1 member-brand partner | Pilot sales |

### C. Mission-amplification (the "why")

| KPI | Target | How measured |
| --- | --- | --- |
| Vet wellness visits driven *(headline)* | Track # wellness-visit redemptions/bookings via card + trackable offers; + self-reported via panel | Card redemptions + offer links + panel survey |
| Vet participation | ≥ 5–10 local vets in directory/card/lead-gen | Partner roster |
| Shelter/adoption engagement | Weekly adoptable features; adoptions/clicks driven; ≥ 2–3 shelter partners | Shelter partners + click tracking |
| Independent-retailer participation | ≥ 5–10 independents featured/in card | Partner roster |
| Housing-operator interest | ≥ 2–3 operators engaged (ties to §B housing line) | Pipeline |
| Advocacy reach / mobilization | Local pet-owner audience reachable for advocacy (size + engagement) | List + engagement |
| Member-brand local connection | ≥ 1 member brand activated locally | Sponsor/JV |

### D. Go/No-Go scorecard (decision rule)

GO if: ≥ 3 of 4 markets clear A (subscribers + open/click) AND ≥ 1 market validates B including ≥ 1 high-margin line (insurance / housing / lead-gen) AND zero factual/YMYL incidents.

Strengtheners (non-gating): strong C mission signals (esp. vet wellness visits), panel opt-in ≥ target, card/event/JV traction.

Otherwise: iterate (pricing/markets/lines) or stop — cheaply.

## Next steps after a GO

Incorporate APPA Ventures (C-corp) + execute arm's-length agreements (brand/data/shared-services; finance via APPA-Stamford).

Commit the staged ~$3M; stand up the shared platform + Ventures CEO/CCO hire.

Sequence regional expansion (~10 cities = a region): fill out the Southeast (core 4 + Asheville/Charleston/Greenville + 3 more) → then Midwest (Kansas City/Omaha/Wichita) and Texas (San Antonio/Waco/Austin).

Write the operator-grade PoC Business Plan on validated MVP data (per the MVP-first sequencing).