# Pets of [City] — MVP Proof-of-Concept Plan (pre-incorporation)

A lean, ~5-month test to validate the riskiest assumptions before incorporating APPA Ventures or committing the staged ~$3M (§D). Run as an internal APPA project/program — no new entity yet. Its only job: generate the evidence for a confident go/no-go.

Framing (per the Competitive Analysis & SWOT): PoC is a local pet utility + community + data business with the newsletter as the funnel — *not* a content/media business. So the MVP must test more than "can we publish & get opens": it must test the durable, high-margin monetization lines (insurance lead-gen, operator-side housing, the data panel) and the community/utility hooks, while ceding national content to Daily Paws/Chewy/Kinship and winning on local truth + community + data.

## 1. Purpose & the riskiest assumptions to test

Don't build the company to find out if the model works — test the things that would kill it (H1–H4), plus a lightweight test of the upside mechanics (H5):

| # | Hypothesis | Why it's the risk |
| --- | --- | --- |
| H1 | Demand — we can acquire engaged local pet-owner subscribers cheaply | If CAC is high, the whole model breaks |
| H2 | Engagement — people actually open/read it weekly | Engagement is the leading indicator of both retention and ad value |
| H3 | Monetization — the durable, high-margin lines (not just ads): can we generate insurance lead-gen, operator-side housing interest, and paid directory/lead-gen — plus ≥1 member-brand sponsor? | The competitive analysis says ads are a thin complement; the margin is in insurance/housing/data/lead-gen — so test *those* |
| H4 | Operations & quality — AI-assisted + human-reviewed weekly content is good, factual, and cheap (no YMYL issues), and one editor can run a market | Tests the unit model and the §B guardrails |
| H5 | Platform-seed signals — early appetite for the §B-Upside streams: a citywide pet discount card (consumers buy / businesses join), a sponsored event, a product-JV "new-owner starter kit", and panel opt-in consent rates | Proves (cheaply) whether the just-in-time platform upside is real before betting on it |

## 2. Scope — 4 MVP core markets (a coherent Southeast region)

The MVP launches the confirmed core 4 — all Southeast, for shared regional advertisers/ops — over 5 months. *(Full footprint & expansion regions: [PoC-Pilot-City-Shortlist.md → Confirmed MVP core](./PoC-Pilot-City-Shortlist.md).)*

| Market | Why this one for the MVP |
| --- | --- |
| Chattanooga, TN ⭐HQ | Headquarters + lead market → in-person ops, founder presence, warm vet relationship. Also the platform-seed market: runs the discount-card, event, and product-JV tests (H5) |
| Brentwood/Franklin, TN | Affluent, highest-pet-spend Williamson County + pet-industry HQ hub (Mars Petcare, Tractor Supply) → tests the member-brand-connection motion (combo edition) |
| Columbia, SC | BCFP-certified, right-size Carolinas market → tests a pure mid-size local edition |
| Raleigh, NC | Warm vet relationship + strong NC pet market → tests the vet-wellness engine; run with neighborhood-level focus (above the right-size zone) |

Vet pipeline: Chattanooga + Raleigh already warm; source warm vet intros in Columbia + Brentwood/Franklin before launch. *(San Antonio moves to the Texas expansion region; Midwest = KC/Omaha/Wichita.)*

Across all four markets: bake panel opt-in / consent (CCPA-class) into the subscribe flow from day one — cheap now, and it preserves the §B-Upside data option (a weak choice to engineer it in later). Concentrate the discount-card / event / JV tests in Chattanooga (HQ) to keep the pilot lean.

## 3. Timeline (~5 months)

| Phase | Weeks | Activities | Output |
| --- | --- | --- | --- |
| 0 · Setup | 1–3 | Pick placeholder brand; stand up newsletter platform (e.g., beehiiv/Substack-class) + analytics; build content templates & AI-assisted workflow with human review; build subscribe flow with panel opt-in / consent; 4-market content calendars; advertiser + vet target lists (incl. sourcing Columbia/Brentwood vet intros); metrics dashboard | Ready to publish; consent baked in |
| 1 · Soft launch | 4–7 | Begin weekly sends in all 4 markets; start paid subscriber acquisition; seed via shelters/vets/partners/social; track panel opt-in rate | First subscribers + baseline engagement + opt-in data |
| 2 · Grow & monetize | 8–16 | Scale acquisition. Test the high-margin lines (H3): place a pet-insurance affiliate/lead-gen unit (esp. to new adopters) and measure leads; pitch operator-side pet-friendly housing to ~3–5 local property managers; sign paid directory/pay-per-lead with vets/groomers; pitch ≥1 member-brand national sponsor (warm via the Williamson County HQ hub). Chattanooga (HQ) platform-seed tests (H5): basic citywide pet discount card (~10–20 businesses, Costco/AAA-style fee + wellness-visit anchor + redemption tracking), one sponsored community event, and a product-JV new-owner starter kit | High-margin-line validation + advertiser + H5 signals |
| 3 · Measure & decide | 17–22 | Analyze vs. go/no-go thresholds; write board decision memo | Go/no-go on incorporating Ventures + committing ~$3M |

## 4. Success metrics & go/no-go thresholds

Measured per market by end of pilot (~month 5). Benchmarks anchored to 6AM City economics (CAC <$1, LTV >$25) and the §B graduation logic (~8–12K subs to staff).

| Metric | Target (per market) | Read |
| --- | --- | --- |
| Subscribers | 3,000–5,000 | On a trajectory toward the ~8–12K staffing threshold |
| Subscriber CAC | ≤ $1.50 | Validates the acquisition model (H1) |
| Open rate | ≥ 40% | Strong for local newsletters (H2) |
| Click rate | ≥ 3% | Real engagement (H2) |
| Unsubscribe / send | < 0.5% | Content-market fit |
| Engagement durability | Open rate holds (no steep decay) over the pilot | Early read on content fatigue (the structural newsletter risk, §B.12a) |
| Advertiser validation | ≥ 2–3 paid pilot sponsors or signed LOIs/market; ≥1 member-brand national sponsor interested | Monetization proof (H3) |
| Insurance lead-gen (high-margin line) | Measurable insurance leads/clicks at a viable effective payout (benchmark $25–152/policy) | Validates the top-margin line (H3) |
| Operator-side housing | ≥ 2–3 property managers express paid interest in pet-housing placement/tools | Validates housing monetization + advocacy (H3) |
| Content quality | Zero factual/YMYL incidents | Guardrails hold (H4) |
| Editor capacity (Chattanooga) | One editor sustains weekly content + sells local sponsors | Unit model works (H4) |
| Vet-wellness (Chattanooga/Raleigh) | Wellness-visit redemptions/bookings driven via card + trackable offers; ≥5–10 participating vets | Mission KPI — the vet-visit engine (de-risked by warm relationships) |
| Panel opt-in (all markets) | ≥ 25–40% of subscribers opt in to research panel | Validates the upside data asset (H5) |
| Discount card (Chattanooga) | ≥ 10–20 participating businesses + meaningful consumer sign-ups + first redemptions | Card demand + foot-traffic proof (H5) |
| Event (Chattanooga) | One event runs at ≥ breakeven with ≥1 paying sponsor | Event-revenue signal (H5) |
| Product JV (Chattanooga) | Starter-kit pilot sells with ≥1 member-brand partner | Product-JV signal (H5) |

Decision rule: GO to incorporate + fund if ≥3 of 4 markets clear the subscriber + engagement thresholds and monetization is validated in ≥1 market (ideally Chattanooga) — including signal on ≥1 high-margin line (insurance lead-gen, operator-side housing, or paid lead-gen), not ads alone. H5 platform-seed results (card/event/JV/panel) are upside evidence that strengthen the case and inform sequencing but are not gating. Otherwise iterate or stop — cheaply.

## 5. Budget (~$200K, 4 core markets + Chattanooga platform-seed + high-margin-line tests, 5 months)

| Line item | Allocation |
| --- | --- |
| Paid subscriber acquisition (4 markets) | $58,000 |
| Local editor (Chattanooga HQ, part-time) + content contributors (Brentwood/Franklin, Columbia, Raleigh) | $45,000 |
| Newsletter platform, AI content tooling, analytics/CRM | $10,000 |
| Panel opt-in / consent + data capture (CCPA-class) build | $8,000 |
| Discount-card pilot (Chattanooga): tooling, merchant onboarding, wellness-visit anchor, redemption tracking | $9,000 |
| Brand placeholder, landing page & email templates (design) | $10,000 |
| Project lead (fractional PM / existing APPA staff time) | $20,000 |
| One sponsored community event (Chattanooga) + product-JV starter-kit pilot | $10,000 |
| High-margin-line tests (insurance affiliate/lead-gen setup, operator-side housing outreach, pay-per-lead tooling) | $5,000 |
| Legal/advisory (sponsorship terms, consent/privacy, JV/affiliate terms; no entity) | $7,000 |
| Contingency (~10%) | $18,000 |
| Total | ~$200,000 |

Leaner alternative (~$110K): 2 markets (Chattanooga + Columbia), heavier AI / lighter paid acquisition, keep only Chattanooga's discount-card + consent tests (drop event/JV) — slower learning but lowest cash while still touching the upside.

Funding: an operating-budget line item / board-approved pilot, well under any threshold requiring entity formation — and a rounding error against the ~$3M it de-risks.

## 6. Team (lean, mostly contract)

Project lead — existing APPA staffer or fractional PM; owns the pilot and the decision memo.

Chattanooga community editor (PT) — HQ-market editor; runs Chattanooga and helps codify the playbook (Raleigh/Columbia/Brentwood-Franklin run AI-assisted with local contributors).

Content/AI contractor — AI-assisted drafting + human/editorial fact-check across all 4 markets.

Freelance designer — brand placeholder, templates, landing page.

Performance-marketing contractor/agency — paid acquisition.

Advisor (optional) — a local-newsletter/media operator for guidance.

## 7. Structure during the MVP (important)

No new entity. Run inside APPA as a program/pilot to avoid premature formation, tax, and overhead.

Keep commercial activity contained: treat early sponsor dollars, discount-card fees, and JV starter-kit sales as modest, contained pilots / program sponsorship, so unrelated-business exposure stays minimal during the test. Scaled ad sales, the full discount card, and data integrations move to APPA Ventures post-go.

Hold the guardrails from day one: no veterinary/medical advice; factual, sourced editorial; sponsors clearly labeled.

Data & consent stewardship from day one: explicit panel opt-in, transparent privacy terms (CCPA-class), and clean separation of consented data — so the §B-Upside data asset is built on a sound, compliant foundation, not retrofitted.

## 8. What the MVP de-risks → the decision it feeds

A successful pilot converts the §D investment case from projection to evidence: real CAC, real open/click rates, real advertiser willingness-to-pay, and a working editor unit. And the H5 platform-seed tests (discount card, event, product JV, panel opt-in) give early read on the §B-Upside — turning the just-in-time-platform vision from speculation into measured signal, and informing what to build first. That is exactly what the board needs to confidently (a) incorporate APPA Ventures, (b) commit the staged ~$3M, and (c) scale via regional expansion — fill out the Southeast region (~10 cities) then replicate to the Midwest and Texas regions — with a data-rich, multi-stream roadmap. A weak pilot saves APPA ~$3M and a year — the entire point of doing it first.